iHub · Risk Clearance Middleware

Full Sprint Roadmap — Sprint 1, 2 & 3

Ceded-Re Project  ·  MRSGt Broker Portal  ·  Agile Story Cards with Hour Estimates

Team Capacity & Estimation Basis

| Sprint Length | Working Days | Dev Hours/Day | Total Capacity |
| --- | --- | --- | --- |
| 3 Weeks | 15 days × 2 devs | 6 hrs (standup/PR/meetings deducted) | 180 hrs total ¦ 90 hrs per dev |
| Ramp note | Dev-B is new to iHub & Databricks. 20% overhead applied to Dev-B stories in Sprint 1, 10% in Sprint 2, zero by Sprint 3. |  |  |

Roadmap Summary

| Sprint | Goal | Dev-A hrs | Dev-B hrs | Total hrs | Stories |
| --- | --- | --- | --- | --- | --- |
| Sprint 1 | Foundation — iHub ingests RX0 payload, builds SQL query, connects to Databricks (mock), returns raw result | 82h | 90h | 172h | 4 |
| Sprint 2 | Processing — Normalisation, aggregation, de-duplication, resilience & partial results to RX0 | 86h | 88h | 174h | 4 |
| Sprint 3 | Hardening — Observability, end-to-end integration with live Databricks, performance, security & prod-readiness | 80h | 82h | 162h | 4 |

Sprint 1 delivers a working but basic pipeline — RX0 payload in, raw result out via mock Databricks.

Sprint 2 adds the full processing layer — normalisation, de-duplication, resilience, and a proven end-to-end test suite.

Sprint 3 hardens for production — observability, live Databricks, performance baseline, security review, and go/no-go sign-off.

Definition of Done (All Stories, All Sprints)

The following criteria must be met before any story can be marked Done. These are non-negotiable from a developer perspective.

| ✓ | Code merged to main branch via approved PR — at least one reviewer sign-off required |
| --- | --- |
| ✓ | All unit tests pass in CI pipeline with zero failures |
| ✓ | Code coverage >= 80% on the story's primary component |
| ✓ | Integration tests pass against mock Databricks adapter |
| ✓ | No critical or high SonarQube / static analysis issues |
| ✓ | Structured logs emitted with correlationId on every code path |
| ✓ | No secrets, credentials, or PII present in code, config, or log output |
| ✓ | All acceptance criteria ticked off and verified by the other developer |
| ✓ | Story demo-able at sprint review against running iHub instance |
| ✓ | Any known technical debt or deferred items raised as backlog items before sprint close |

Risk Register

| # | Risk | Likelihood | Impact | Mitigation |
| --- | --- | --- | --- | --- |
| 1 | Dev-B ramp time on Databricks/iHub underestimated | High | High | 20% buffer added to all Dev-B Sprint 1 stories. Dev-A pairs with Dev-B on IH-004 mock adapter for first 2 days. Daily sync on blockers. |
| 2 | Live Databricks schema differs from mock adapter data model | Medium | High | Dev-A to review live schema in Sprint 1 Day 1 and align mock adapter. Schema diff document maintained throughout. |
| 3 | Databricks firewall/network access not ready for Sprint 3 | Medium | High | Raise with DevOps (Shah Darshan) at Sprint 3 kickoff. Mock adapter ensures Sprints 1 & 2 are unblocked regardless. |
| 4 | IH-003 SQL Query Builder overruns — cascades to IH-004/IH-005 | Medium | High | IH-003 is highest-complexity story. Flag immediately if > 2 days behind. Descope fuzzy match to Sprint 2 if needed. |
| 5 | RX0 payload contract changes mid-sprint | Low | Medium | Freeze RX0 contract at Sprint 1 kickoff. Any changes go through change control and assessed for sprint impact. |
| 6 | Performance SLA not agreed before Sprint 3 | Medium | Medium | Raise SLA conversation with business/SA in Sprint 2. Cannot run IH-011 without an agreed target. |
| 7 | Security issues found in Sprint 3 delay production | Low | High | Dev-A conducts light-touch security review during Sprint 2 PRs. Reduces surprises in Sprint 3 IH-012. |

Sprint 1

Foundation — Payload Ingestion · SQL Query Builder · Databricks Connectivity

Sprint Goal: iHub can receive a valid RX0 Risk Clearance request, validate all parameters, generate the correct SQL query, execute it against the mock Databricks adapter, and return the raw result. The mock adapter is production-schema-aligned. Dev-B has completed iHub/Databricks onboarding.

Capacity — Sprint 1

| Dev-A (familiar) | Dev-B (new · +20% ramp) | Sprint 1 Total |
| --- | --- | --- |
| 82h | 90h (incl. ~15h ramp buffer) | 172h |

2-Developer Swimlane — Sprint 1

| Week / Day | Dev-A | Dev-B |
| --- | --- | --- |
| Wk1 · Day 1–2 | IH-001: Intake contract design · payload parser build | IH-001: Contract review · negative-path tests (ramp activity) |
| Wk1 · Day 3–5 | IH-002: Define all validation rules · edge case doc | IH-002: Validation layer build (ramp: +2h buffer) |
| Wk2 · Day 1–3 | IH-003: Query builder architecture · exact/fuzzy strategies | IH-003: Unit tests for SQL output · SQL injection review (ramp: +2h buffer) |
| Wk2 · Day 4–5 | IH-003: LOB/limit/lookback filters · finalise | IH-004: Mock adapter build begins (pair with Dev-A Day 5) |
| Wk3 · Day 1–3 | IH-004: Live Databricks connector · connection config · pooling | IH-004: Mock adapter · config-driven switch · test data schema (ramp: +4h buffer) |
| Wk3 · Day 4–5 | IH-004: Connection error handling · smoke test (joint) | IH-004: Mock verification · smoke test (joint) |

Story Cards — Sprint 1

| IH-001 iHub Intake Contract & RX0 Payload Parser |  |
| --- | --- |
| Owner | Dev-A |
| Priority | High |
| Estimate | Dev-A: 16h Dev-B: 8h Total: 24h |
| Description | Define the iHub intake contract for Risk Clearance requests from RX0. Build the payload parser that deserialises the RX0 message into iHub's internal request model. Dev-B reviews contract and writes negative-path tests. |
| Dev Tasks |  |
|  | - Define intake contract: all fields, types, enums, required vs optional (Dev-A · 4h) |
|  | - Build payload deserialiser: RX0 JSON → iHub internal request model (Dev-A · 6h) |
|  | - Build structured error response for malformed/missing fields back to RX0 (Dev-A · 4h) |
|  | - Dev-B: review contract for consumer accuracy, raise gaps (Dev-B · 4h) |
|  | - Dev-B: write negative-path unit tests — missing field, wrong type, unknown field (Dev-B · 4h) [ramp: +2h buffer] |
|  | - PR review and merge (both · 2h) |
| Acceptance Criteria (DoD) |  |
|  | - Intake contract document published to repo and reviewed by Dev-B |
|  | - Valid RX0 payload deserialises correctly into internal model with all fields mapped |
|  | - Missing required field returns structured 400 error with field-level detail to RX0 |
|  | - Unknown/extra fields are silently ignored (no crash) |
|  | - Internal model is decoupled — no RX0 types leak into iHub core |
|  | - Unit test coverage >= 90% on parser |
|  | - PR approved by both developers before merge |

| IH-002 Request Validation & Parameter Enforcement |  |
| --- | --- |
| Owner | Dev-B |
| Priority | High |
| Estimate | Dev-A: 6h Dev-B: 22h Total: 28h |
| Description | Validate all parameters from the parsed internal model. Enforce rules for system, lookback, search type (exact/fuzzy), confidence threshold, LOB=PVT, and result limits. Dev-B implements; Dev-A defines the rule set and reviews edge cases. |
| Depends On | IH-001 |
| Risk | Dev-B is new — allow extra review cycles. Dev-A must have rule set doc ready Day 1. |
| Dev Tasks |  |
|  | - Dev-A: document all validation rules, allowed enums, ranges, and interdependencies (Dev-A · 4h) |
|  | - Build validation layer on top of IH-001 internal model (Dev-B · 8h) [ramp: +2h buffer] |
|  | - Implement LOB=PVT enforcement with 400 + machine-readable error code (Dev-B · 3h) |
|  | - Validate confidence threshold (0.0–1.0), result limit (1–100), lookback range (Dev-B · 3h) |
|  | - Validate exact/fuzzy enum values (Dev-B · 2h) |
|  | - Dev-A: review edge case handling and error response format (Dev-A · 2h) |
|  | - Unit tests: all rules including boundary values (Dev-B · 4h) |
| Acceptance Criteria (DoD) |  |
|  | - All required parameters validated before any downstream processing begins |
|  | - LOB=PVT violation returns 400 with machine-readable error code — no downstream call made |
|  | - Confidence threshold outside 0.0–1.0 rejected with clear error message |
|  | - Result limit outside 1–100 rejected |
|  | - Invalid search type enum returns 400 |
|  | - All validation rules documented in code comments |
|  | - Unit tests cover all rules including every boundary value |
|  | - Zero downstream calls fired for any invalid request |

| IH-003 Dynamic SQL Query Builder |  |
| --- | --- |
| Owner | Dev-A |
| Priority | High |
| Estimate | Dev-A: 30h Dev-B: 14h Total: 44h |
| Description | Build the component that converts the validated iHub internal model into a parameterised SQL query for Databricks. Must handle all search types, LOB filters, lookback date ranges, result limits, and exact/fuzzy strategies. This is the most complex story in Sprint 1. |
| Depends On | IH-002 |
| Risk | Highest complexity story in Sprint 1. If Dev-A is blocked here it cascades to IH-004 and IH-005. Flag immediately if > 2 days behind. |
| Dev Tasks |  |
|  | - Design query builder architecture — strategy pattern per search type (Dev-A · 4h) |
|  | - Implement base parameterised query builder (Dev-A · 6h) |
|  | - Implement exact match query strategy (Dev-A · 4h) |
|  | - Implement fuzzy match query strategy (Dev-A · 5h) |
|  | - Implement lookback period → date range filter (Dev-A · 3h) |
|  | - Implement LOB, system, result limit filters (Dev-A · 4h) |
|  | - Query targets Policies, Quotes, Submissions tables correctly (Dev-A · 4h) |
|  | - Dev-B: write unit tests for query output across 8 distinct scenarios (Dev-B · 8h) [ramp: +2h buffer] |
|  | - Dev-B: SQL injection review — verify all params are escaped/bound (Dev-B · 4h) |
|  | - PR review and merge (both · 2h) |
| Acceptance Criteria (DoD) |  |
|  | - SQL generated dynamically — zero hard-coded query strings |
|  | - All parameters map correctly to SQL clauses |
|  | - Exact and fuzzy match produce demonstrably different query strategies |
|  | - Lookback period correctly translates to a bounded date range in SQL |
|  | - All parameters are bound (not string-concatenated) — SQL injection not possible |
|  | - Query targets correct tables for Policies, Quotes, and Submissions |
|  | - Unit tests cover: exact, fuzzy, each LOB, min/max result limit, longest lookback period |
|  | - Dev-B code review sign-off confirming SQL safety |

| IH-004 Databricks Connectivity & Mock Adapter |  |
| --- | --- |
| Owner | Dev-A |
| Priority | High |
| Estimate | Dev-A: 30h Dev-B: 46h Total: 76h |
| Description | Build the Databricks connector in iHub. Externalise connection config per environment (Dev/QA/UAT/Prod). Build a mock Databricks adapter for Sprint 1 & 2 testing. Dev-B owns mock adapter and environment config wiring as a primary ramp activity. |
| Depends On | IH-003 |
| Risk | Dev-B ramp risk highest here. Dev-A should pair with Dev-B on mock adapter for first 2 days of this story. |
| Dev Tasks |  |
|  | - Dev-A: build live Databricks connector — executes parameterised SQL, returns raw result set (Dev-A · 14h) |
|  | - Dev-A: connection config externalised per environment — no hard-coded credentials (Dev-A · 6h) |
|  | - Dev-A: connection error handling — Databricks exceptions mapped to iHub error model (Dev-A · 4h) |
|  | - Dev-A: connection pooling / reuse strategy (Dev-A · 6h) |
|  | - Dev-B: build mock Databricks adapter — realistic test data for P/Q/S (Dev-B · 16h) [ramp: +4h buffer] |
|  | - Dev-B: config-driven switch between live and mock adapter (feature flag / env var) (Dev-B · 8h) [ramp: +2h buffer] |
|  | - Dev-B: verify all unit tests run fully against mock with zero live Databricks dependency (Dev-B · 8h) [ramp: +2h buffer] |
|  | - Dev-B: document mock data schema so it stays in sync with real Databricks schema (Dev-B · 4h) |
|  | - Integration smoke test: IH-001 → IH-002 → IH-003 → IH-004 mock → raw result returned (both · 6h) |
| Acceptance Criteria (DoD) |  |
|  | - Live connector executes parameterised SQL and returns raw result set correctly |
|  | - All connection config is environment-specific and externalised (no secrets in code) |
|  | - Mock adapter returns realistic Policies, Quotes, Submissions test data |
|  | - Switching between live and mock requires only a config/env change — no code change |
|  | - Raw Databricks exceptions never bubble up to RX0 — always mapped to iHub error model |
|  | - All Sprint 1 unit and integration tests run against mock adapter only |
|  | - End-of-sprint smoke test: full IH-001 to IH-004 pipeline returns raw result from mock |
|  | - Mock data schema documented and version-controlled |

Sprint 2

Processing — Normalisation · Aggregation · De-duplication · Resilience · E2E Test Gate

Sprint Goal: iHub processes Databricks results end-to-end — normalised, aggregated, de-duplicated, and resilient. Partial results and errors are returned correctly to RX0. A full integration test suite passes across 8 scenarios. No known bugs carried to Sprint 3.

Capacity — Sprint 2

| Dev-A | Dev-B (10% ramp buffer remains) | Sprint 2 Total |
| --- | --- | --- |
| 86h | 88h | 174h |

2-Developer Swimlane — Sprint 2

| Week / Day | Dev-A | Dev-B |
| --- | --- | --- |
| Wk1 · Day 1–2 | IH-005: Define common result model (must be done first) | IH-005: Policies mapping (after model agreed) |
| Wk1 · Day 3–5 | IH-005: Review mappings · integration test | IH-005: Quotes + Submissions mapping · null handling |
| Wk2 · Day 1–2 | IH-006: De-dup key strategy · prioritisation config | IH-006: Aggregation build · de-dup implementation |
| Wk2 · Day 3–5 | IH-007: Timeout · retry with backoff · partial result logic | IH-006: Prioritisation rules · unit tests · IH-006 PR |
| Wk3 · Day 1–3 | IH-007: Circuit breaker · full failure handling | IH-007: Integration tests (timeout, CB trip, partial result) |
| Wk3 · Day 4–5 | IH-008: E2E test design · happy path · exact/fuzzy/lookback tests | IH-008: Validation failure · partial · full failure · CB tests |

Story Cards — Sprint 2

| IH-005 Result Normalisation |  |
| --- | --- |
| Owner | Dev-B |
| Priority | High |
| Estimate | Dev-A: 14h Dev-B: 24h Total: 38h |
| Description | Map raw Databricks results into iHub's common result model. Dev-A defines the model; Dev-B implements the mapping for Policies, Quotes, and Submissions. Handles partial and null results gracefully. |
| Depends On | IH-004 |
| Dev Tasks |  |
|  | - Dev-A: define common result model — all fields, types, nullable rules (Dev-A · 6h) |
|  | - Dev-A: review and sign off Dev-B's mapping implementation (Dev-A · 4h) |
|  | - Dev-A: integration test — normalised output verified end-to-end (Dev-A · 4h) |
|  | - Dev-B: implement Policies mapping: raw Databricks schema → common model (Dev-B · 6h) |
|  | - Dev-B: implement Quotes mapping (Dev-B · 5h) |
|  | - Dev-B: implement Submissions mapping (Dev-B · 5h) |
|  | - Dev-B: handle null/missing fields from Databricks without crashing (Dev-B · 3h) |
|  | - Dev-B: unit tests — full result, partial result, empty result per source type (Dev-B · 5h) |
| Acceptance Criteria (DoD) |  |
|  | - Common result model defined, documented, and agreed by both devs before coding starts |
|  | - All three mappings (Policies, Quotes, Submissions) produce conformant common model output |
|  | - Null or missing Databricks fields handled gracefully — no NullPointerException or equivalent |
|  | - Partial Databricks response (e.g. only Policies returned) normalised without error |
|  | - Unit tests cover: full data, 1 source missing, all sources empty |
|  | - Dev-A sign-off on common model before Dev-B begins mapping |

| IH-006 Aggregation & De-duplication |  |
| --- | --- |
| Owner | Dev-B |
| Priority | High |
| Estimate | Dev-A: 12h Dev-B: 24h Total: 36h |
| Description | Aggregate normalised results across Policies, Quotes, and Submissions into a single result set. Identify and remove duplicates using an agreed key. Apply configurable prioritisation rules. |
| Depends On | IH-005 |
| Dev Tasks |  |
|  | - Dev-A: define de-duplication key strategy (e.g. policy ref + source system + risk ID) (Dev-A · 4h) |
|  | - Dev-A: define prioritisation order and make it config-driven (Dev-A · 4h) |
|  | - Dev-A: review de-dup implementation and edge cases (Dev-A · 4h) |
|  | - Dev-B: implement aggregation — combine P/Q/S into unified collection (Dev-B · 6h) |
|  | - Dev-B: implement de-duplication using agreed key (Dev-B · 7h) |
|  | - Dev-B: implement configurable prioritisation (Policy > Quote > Submission default) (Dev-B · 5h) |
|  | - Dev-B: log removed duplicates with correlationId for traceability (Dev-B · 2h) |
|  | - Dev-B: unit tests — no dupes, multi-source dupes, all-duplicate set (Dev-B · 4h) |
| Acceptance Criteria (DoD) |  |
|  | - De-duplication key agreed and documented before implementation |
|  | - Duplicate records removed — only highest-priority record retained per group |
|  | - Prioritisation order is config-driven — changing it requires no code change |
|  | - Removed duplicates written to log with correlationId |
|  | - Aggregation handles any combination of empty/partial source results |
|  | - Unit tests: single source, multi-source with dupes, full overlap across all 3 sources |

| IH-007 Resilience — Timeouts, Retries & Circuit Breaker |  |
| --- | --- |
| Owner | Dev-A |
| Priority | High |
| Estimate | Dev-A: 36h Dev-B: 16h Total: 52h |
| Description | Implement per-call timeouts, retry logic with backoff, and a circuit breaker for the Databricks connection. Return partial results with error codes to RX0 when Databricks fails or times out. iHub must never block RX0 indefinitely. |
| Depends On | IH-004 |
| Risk | Circuit breaker testing requires mock that can simulate failure sequences. Dev-B must extend mock adapter from IH-004 to support this. |
| Dev Tasks |  |
|  | - Implement per-call timeout — configurable per environment, default 5s (Dev-A · 6h) |
|  | - Implement retry policy — max 2 retries, exponential backoff (Dev-A · 8h) |
|  | - Implement circuit breaker — trips after 3 consecutive failures, auto-resets after cooldown (Dev-A · 10h) |
|  | - Implement partial result response — failed sources excluded, error codes attached (Dev-A · 8h) |
|  | - Ensure full Databricks failure returns structured error to RX0, never raw exception (Dev-A · 4h) |
|  | - Dev-B: write integration tests — timeout scenario, circuit breaker trip, partial result (Dev-B · 10h) |
|  | - Dev-B: validate all error codes align with IH-001 intake contract (Dev-B · 6h) |
| Acceptance Criteria (DoD) |  |
|  | - Per-call timeout fires correctly and is configurable without code change |
|  | - Retry fires max 2 times with observable backoff delay between attempts |
|  | - Circuit breaker trips after 3 consecutive Databricks failures |
|  | - Circuit breaker auto-resets after configurable cooldown — verified in test |
|  | - Partial result returned to RX0 with source-level error codes when one source fails |
|  | - Full failure returns structured 503-equivalent error to RX0 — never a raw stack trace |
|  | - RX0 is never left waiting beyond timeout + retry window |
|  | - Integration tests: timeout → partial result, circuit open → immediate error, retry success on 2nd attempt |

| IH-008 End-to-End Integration Test (Sprint 2 Gate) |  |
| --- | --- |
| Owner | Dev-A |
| Priority | High |
| Estimate | Dev-A: 24h Dev-B: 24h Total: 48h |
| Description | Build the full end-to-end integration test suite covering the complete iHub pipeline: RX0 payload → parse → validate → SQL build → Databricks (mock) → normalise → aggregate → de-duplicate → resilience → response to RX0. This is the Sprint 2 exit gate. |
| Depends On | IH-005, IH-006, IH-007 |
| Dev Tasks |  |
|  | - Design integration test scenarios — agree list of 8 key scenarios (both · 4h) |
|  | - Happy path: valid request → full result returned to RX0 (Dev-A · 4h) |
|  | - Validation failure: invalid LOB → structured 400 returned, no DB call (Dev-B · 3h) |
|  | - Partial result: one Databricks source times out → partial result + error code to RX0 (Dev-A · 4h) |
|  | - Full failure: all sources fail → structured error response to RX0 (Dev-B · 4h) |
|  | - De-duplication: multi-source result with known dupes → correct single record returned (Dev-A · 4h) |
|  | - Circuit breaker: 3 consecutive failures → circuit opens → subsequent calls fail fast (Dev-B · 4h) |
|  | - Exact vs fuzzy: verify different SQL strategies produce different result sets (Dev-A · 4h) |
|  | - Lookback boundary: verify date range filter correct for min/max lookback (Dev-B · 4h) |
|  | - Test report generated and reviewed by both devs (both · 2h) |
| Acceptance Criteria (DoD) |  |
|  | - All 8 integration scenarios pass consistently |
|  | - All tests run against mock Databricks adapter — zero live dependency |
|  | - Full pipeline observable via structured logs with correlationId on every test run |
|  | - No test relies on hard-coded data — test data driven from mock adapter config |
|  | - Test report produced and signed off by both developers |
|  | - Zero known bugs carried into Sprint 3 |

Sprint 3

Hardening — Observability · Live Databricks · Performance · Security · Production Readiness

Sprint Goal: iHub is production-ready. Structured logging with full trace propagation is in place. Live Databricks is validated in Dev and QA. Performance meets the agreed SLA. Security review is complete. A signed-off go/no-go checklist exists for production deployment.

Capacity — Sprint 3

| Dev-A | Dev-B (fully ramped) | Sprint 3 Total |
| --- | --- | --- |
| 80h | 82h | 162h |

2-Developer Swimlane — Sprint 3

| Week / Day | Dev-A | Dev-B |
| --- | --- | --- |
| Wk1 · Day 1–2 | IH-009: correlationId scheme · trace propagation to Databricks | IH-009: Structured JSON logging across all components |
| Wk1 · Day 3–5 | IH-010: Live schema validation · SQL queries against Dev cluster | IH-009: Log levels · exec time · PII audit · unit test |
| Wk2 · Day 1–3 | IH-010: Schema fix · connection pooling · CB on live cluster | IH-010: Env config validation · integration tests on live Dev |
| Wk2 · Day 4–5 | IH-011: Pipeline timing instrumentation · baseline test run | IH-010: Live vs mock discrepancy doc |
| Wk3 · Day 1–2 | IH-011: Bottleneck optimisation (top 2) · perf report | IH-011: Load test scenarios · p50/p95/p99 results doc |
| Wk3 · Day 3–5 | IH-012: SQL injection re-check · auth review · secrets audit | IH-012: PII audit · error response check · readiness checklist · go/no-go |

Story Cards — Sprint 3

| IH-009 Structured Logging, Observability & Trace Propagation |  |
| --- | --- |
| Owner | Dev-B |
| Priority | High |
| Estimate | Dev-A: 14h Dev-B: 24h Total: 38h |
| Description | Implement structured JSON logging throughout the full iHub pipeline. Propagate correlationId from the RX0 request through all processing steps and into the Databricks query. Dev-A defines the correlationId scheme. |
| Depends On | IH-008 |
| Dev Tasks |  |
|  | - Dev-A: define correlationId origination — from RX0 header or generated by iHub if absent (Dev-A · 4h) |
|  | - Dev-A: ensure correlationId propagates into Databricks query call (Dev-A · 4h) |
|  | - Dev-A: review log output across full pipeline (Dev-A · 4h) |
|  | - Dev-A: review Dev-B implementation for PII leakage (Dev-A · 2h) |
|  | - Dev-B: implement structured JSON logging across all IH-001 to IH-008 components (Dev-B · 10h) |
|  | - Dev-B: log levels — INFO for flow, DEBUG for detail, WARN/ERROR for issues (Dev-B · 3h) |
|  | - Dev-B: log query execution time per Databricks call (Dev-B · 3h) |
|  | - Dev-B: audit all log statements for PII — remove any sensitive data (Dev-B · 4h) |
|  | - Dev-B: unit test confirming correlationId present on all log entries for a pipeline run (Dev-B · 4h) |
| Acceptance Criteria (DoD) |  |
|  | - All log entries are structured JSON — no plain text log strings anywhere |
|  | - correlationId present on every log entry from request receipt to RX0 response dispatch |
|  | - correlationId propagated into Databricks call and visible in query logs |
|  | - Query execution time logged per Databricks call |
|  | - Log levels used consistently and correctly across all components |
|  | - PII audit completed — no names, policy holders, or credentials in any log output |
|  | - Unit test confirms correlationId present end-to-end on a sample run |

| IH-010 Live Databricks Integration & Environment Validation |  |
| --- | --- |
| Owner | Dev-A |
| Priority | High |
| Estimate | Dev-A: 30h Dev-B: 20h Total: 50h |
| Description | Switch iHub from mock Databricks adapter to live Databricks in Dev and QA environments. Validate queries, schema alignment, and connection behaviour. Dev-B validates environment config and runs regression tests against live data. |
| Depends On | IH-008, IH-009 |
| Risk | Live Databricks access may require firewall/network changes. Raise with DevOps (Shah Darshan) at Sprint 3 kickoff — do not wait. |
| Dev Tasks |  |
|  | - Dev-A: validate live Databricks schema matches mock adapter data model (Dev-A · 6h) |
|  | - Dev-A: run all SQL queries from IH-003 against live Dev Databricks cluster (Dev-A · 6h) |
|  | - Dev-A: fix any schema mismatches between mock and live (Dev-A · 8h) |
|  | - Dev-A: validate connection pooling under sustained load in Dev environment (Dev-A · 6h) |
|  | - Dev-A: verify circuit breaker and timeout behaviour against live cluster (Dev-A · 4h) |
|  | - Dev-B: validate environment config correct for Dev and QA (Dev-B · 6h) |
|  | - Dev-B: run integration test suite from IH-008 against live Databricks in Dev (Dev-B · 8h) |
|  | - Dev-B: document any live vs mock discrepancies and raise as backlog items if not fixable this sprint (Dev-B · 6h) |
| Acceptance Criteria (DoD) |  |
|  | - Live Databricks queries execute correctly for all search types in Dev environment |
|  | - Schema alignment confirmed — no field mapping errors between mock and live |
|  | - All IH-008 integration tests pass against live Databricks in Dev environment |
|  | - Circuit breaker and timeout behaviour confirmed with live cluster |
|  | - Environment config verified for Dev and QA — no secrets in code |
|  | - Any live vs mock discrepancies documented |

| IH-011 Performance Baseline & Query Optimisation |  |
| --- | --- |
| Owner | Dev-A |
| Priority | Medium |
| Estimate | Dev-A: 24h Dev-B: 14h Total: 38h |
| Description | Establish a performance baseline for the iHub pipeline against live Databricks. Identify slow queries or bottlenecks. Optimise where needed to meet the agreed SLA. Dev-B runs load scenarios and documents results. |
| Depends On | IH-010 |
| Dev Tasks |  |
|  | - Agree performance SLA with business/SA: target response time under normal load (both · 2h) |
|  | - Dev-A: instrument pipeline with timing metrics at each stage (Dev-A · 4h) |
|  | - Dev-A: run baseline performance test — 10, 50, 100 concurrent requests (Dev-A · 6h) |
|  | - Dev-A: identify slow stages — query build, Databricks round-trip, normalisation (Dev-A · 4h) |
|  | - Dev-A: optimise top 2 bottlenecks identified (Dev-A · 8h) |
|  | - Dev-B: design and run load test scenarios using mock and live adapters (Dev-B · 8h) |
|  | - Dev-B: document results — p50, p95, p99 response times per scenario (Dev-B · 6h) |
| Acceptance Criteria (DoD) |  |
|  | - Performance SLA agreed and documented before testing begins |
|  | - Baseline test run at 10, 50, and 100 concurrent requests — results documented |
|  | - p95 response time meets agreed SLA under 50 concurrent request load |
|  | - Top 2 bottlenecks identified and addressed |
|  | - Performance test results (p50/p95/p99) published to sprint artefacts |
|  | - No regression in correctness after any optimisation — all IH-008 tests still pass |

| IH-012 Security Review, Hardening & Production Readiness |  |
| --- | --- |
| Owner | Dev-B |
| Priority | High |
| Estimate | Dev-A: 12h Dev-B: 24h Total: 36h |
| Description | Conduct a security review of the full iHub pipeline. Harden against identified risks. Validate production configuration. Produce a deployment readiness checklist. This is the Sprint 3 exit gate and the production go/no-go checkpoint. |
| Depends On | IH-009, IH-010, IH-011 |
| Risk | Security issues found late can delay production. Dev-A should do a light-touch security review during Sprint 2 to avoid Sprint 3 surprises. |
| Dev Tasks |  |
|  | - Dev-A: review SQL query builder for injection risks — second pass after IH-003 (Dev-A · 4h) |
|  | - Dev-A: review auth between RX0 → iHub and iHub → Databricks (Dev-A · 4h) |
|  | - Dev-A: confirm no secrets or credentials exist anywhere in codebase or logs (Dev-A · 4h) |
|  | - Dev-B: conduct full PII audit across pipeline — request, response, logs (Dev-B · 6h) |
|  | - Dev-B: validate all error responses to RX0 contain no internal stack traces (Dev-B · 4h) |
|  | - Dev-B: produce deployment readiness checklist (Dev-B · 6h) |
|  | - Dev-B: validate UAT environment config (Dev-B · 4h) |
|  | - Dev-B: produce go/no-go checklist for production deployment (Dev-B · 4h) |
|  | - Final joint review of all artefacts (both · 4h) |
| Acceptance Criteria (DoD) |  |
|  | - SQL injection review completed — no vulnerabilities found or all found issues resolved |
|  | - Auth review completed for RX0→iHub and iHub→Databricks connections |
|  | - Zero secrets or credentials found anywhere in code, config, or logs |
|  | - PII audit completed — no personal data in logs, error responses, or internal models beyond what is required |
|  | - All error responses to RX0 verified — no internal stack traces exposed |
|  | - Deployment readiness checklist completed and signed off by both developers |
|  | - UAT environment config validated |
|  | - Go/no-go production checklist produced and reviewed with Solution Architect (Jon) |